## Cover
Broken Arrow Training App
IT Project Plan v1.0 - Sprint Tracker
Document Version | 1.0
Created | 2026-04-20
Authored By | Mike (product) with Claude
Planning Horizon | 6 months (26 weeks / 13 x 2-week sprints)
Target Start | 2026-04-27
Target End | 2026-10-25
Scope | 4 gap engines (Terrain completion, MIM novel IP, Descent-Load, Altitude) + Foundation + Integration/Release
Companion Doc | docs/PROJECT_PLAN.md
Strategic Inputs | BA_Executive_Summary_v3.html, BA_Vector1_Science_v3.html, BA_Strategic_Plan_v3.html, BA_DataFlow_v2.html
Sheet | Contents
Overview | High-level phase summary with KPI counts (formula-driven)
Phases | 6 phases with sprints and calendar windows
Sprints | 13 sprints with goal, deliverables, owner, status
User_Stories | 37 INVEST-form user stories with priority + points
Acceptance_Criteria | Gherkin (Given/When/Then) ACs per user story
Tasks | Claude Code engineering tasks with file paths per sprint
QA_Checklist | Sprint-specific QA items (science, perf, a11y, privacy, release)
Test_Matrix | Unit / integration / regression / E2E tests per sprint
Risk_Register | Plan-level + sprint-level risks with probability x impact
References | 18 peer-reviewed citations with PMIDs
Glossary | 24 term abbreviations

## Overview
Overview - counts by status and phase (formula-driven)
Metric | Count | Planned | In Progress | Done | Source
Sprints total | 13 | 13 | 0 | 0 | Sprints sheet column I
Phases total | 6 | - | - | - | Phases sheet
User stories total | 37 | 37 | 0 | 0 | User_Stories sheet column G
Tasks total | 66 | 66 | 0 | 0 | Tasks sheet column F
QA items total | 67 | - | - | - | QA_Checklist sheet
Test matrix rows | 55 | - | - | - | Test_Matrix sheet
Risks total | 40 | 28 | 12 | 0 | Risk_Register sheet column H
References total | 18 | - | - | - | References sheet
Glossary terms total | 24 | - | - | - | Glossary sheet
Sprints by phase (formula-driven)
Phase ID | Phase Name | Sprint Count | First Sprint | Last Sprint | Calendar Window
P0 | Foundation | 1 | 1 | 1 | 2026-04-27 to 2026-05-10
P1 | Terrain Engine | 3 | 2 | 4 | 2026-05-11 to 2026-06-21
P2 | MIM (Novel IP) | 3 | 5 | 7 | 2026-06-22 to 2026-08-02
P3 | Descent-Load | 2 | 8 | 9 | 2026-08-03 to 2026-08-30
P4 | Altitude | 2 | 10 | 11 | 2026-08-31 to 2026-09-27
P5 | Integration & Release | 2 | 12 | 13 | 2026-09-28 to 2026-10-25

## Phases
Phases
Phase ID | Name | First Sprint | Last Sprint | Start | End | Description
P0 | Foundation | 1 | 1 | 2026-04-27 | 2026-05-10 | Cross-cutting scaffolding: engine module boundary, feature store, DEM adapter, evidence tiers, coverage gate
P1 | Terrain Engine | 2 | 4 | 2026-05-11 | 2026-06-21 | GAP via Minetti 2002, DEM correction, vertical efficiency, UTMB/ITRA index
P2 | MIM (Novel IP) | 5 | 7 | 2026-06-22 | 2026-08-02 | Bayesian partial-pooled MIM with population priors, per-user personalisation, evidence-tier UI, methodology doc
P3 | Descent-Load | 8 | 9 | 2026-08-03 | 2026-08-30 | Eccentric-TRIMP (Vernillo 2017) and repeated-bout memory (Hyldahl 2017)
P4 | Altitude | 10 | 11 | 2026-08-31 | 2026-09-27 | Hypoxic dose, acclimatization sigmoid (Levine 1997), intensity dampening (West 2013), AMS advisory (Bailey 2021)
P5 | Integration & Release | 12 | 13 | 2026-09-28 | 2026-10-25 | Adaptive Plan Engine ensembles all 5 engines; LLM grounding; release hardening; v1.0.0

## Sprints
Sprints (13 x 2-week, 2026-04-27 to 2026-10-25)
# | Name | Phase | Start | End | Goal | Key Deliverables | Owner | Status
1 | Foundation | P0 | 2026-04-27 | 2026-05-10 | De-risk downstream sprints with scaffolding | src/engines/ module; featureStore; DEM adapter; evidence tiers; coverage gate; ADR 0001 & 0002 | Claude Code + Mike | Planned
2 | Terrain-A (GAP / Minetti) | P1 | 2026-05-11 | 2026-05-24 | Grade-Adjusted Pace per Minetti 2002 | minetti.ts; gap.ts; ActivityCard GAP display | Claude Code | Planned
3 | Terrain-B (DEM correction) | P1 | 2026-05-25 | 2026-06-07 | Replace device elevation with DEM-snapped elevation | dem.ts; usgs3DEP / srtm / asterGDEM adapters; tileCache; CF Worker proxy | Claude Code | Planned
4 | Terrain-C (VE + UTMB Index) | P1 | 2026-06-08 | 2026-06-21 | Vertical efficiency + UTMB/ITRA indexes | ve.ts; utmbIndex.ts; itraIndex.ts; Terrain dashboard card | Claude Code | Planned
5 | MIM-A (Priors + Bayes scaffold) | P2 | 2026-06-22 | 2026-07-05 | Population priors + Bayesian posterior in shadow mode | priors.json; bayes.ts; fit-mim-priors.ts; shadow-mode flag | Claude Code + Mike | Planned
6 | MIM-B (Personalisation loop) | P2 | 2026-07-06 | 2026-07-19 | Soreness prompt + nightly posterior update, cohort flip | SorenessPrompt; update-posteriors.py; learner.ts; cohort service | Claude Code + Mike | Planned
7 | MIM-C (Evidence-tier UI + methodology) | P2 | 2026-07-20 | 2026-08-02 | Explainability UI + methodology doc + 100% rollout | MIMEvidenceBadge.tsx; mim-methodology.md; canary runbook | Claude Code + Mike | Planned
8 | Descent-A (Eccentric-TRIMP) | P3 | 2026-08-03 | 2026-08-16 | Eccentric dose per descent bucket | eccentric.ts; TRIMPRecord extension; Eccentric load strip | Claude Code | Planned
9 | Descent-B (Repeated-bout memory) | P3 | 2026-08-17 | 2026-08-30 | Protection factor for back-to-back bouts | boutMemory.ts; readiness integration; ADR 0003 | Claude Code | Planned
10 | Altitude-A (Dose + Sigmoid) | P4 | 2026-08-31 | 2026-09-13 | Hypoxic dose accumulator + acclimatization sigmoid | dose.ts; acclimatization.ts; AltitudeTripForm | Claude Code + Mike | Planned
11 | Altitude-B (Dampening + AMS) | P4 | 2026-09-14 | 2026-09-27 | VO2max-loss dampening + AMS advisory | dampening.ts; ams.ts; CoachSnapshot altitude | Claude Code + Mike | Planned
12 | Ensemble (Adaptive Plan Engine) | P5 | 2026-09-28 | 2026-10-11 | Compose 5 engines into DailyPrescription + LLM grounding | adaptive/index.ts; ADR 0004; coachGolden tests; Why-this-workout card | Claude Code + Mike | Planned
13 | Release hardening | P5 | 2026-10-12 | 2026-10-25 | Performance, offline-first, a11y, release v1.0.0 | tinybench perf suite; axe-core CI; release runbook; CHANGELOG.md; v1.0.0 tag | Claude Code + Mike | Planned

## Preservation
Preservation Matrix — shipped code ↔ plan decisions
No shipped feature is silently dropped. Every row below names a surface in the shipped app and the decision the plan takes. Mirrors PROJECT_PLAN.md §4.4.
Legend: ✅ Preserve = unchanged · 🔄 Extend = kept + additive props · 📦 Re-parent = kept, moved · ✂ Streamline = content consolidated · 🆕 Add = net-new · ❌ Deprecate = replaced (justified)
Group | Shipped surface | Decision | Sprint that touches | File path | Notes
Summary tab | TodayBriefing | 🔄 Extend | S12 | src/components/TodayBriefing.tsx | Riley hero card wraps it; 'Why' collapsible gains MIM + Altitude bullets
Summary tab | VitalsGrid | ✅ Preserve | — | src/components/VitalsGrid.tsx | HRV / RHR / Sleep / Body Battery with sparklines. No change.
Summary tab | InjuryRiskAlerts | 🔄 Extend | S8, S11 | src/components/InjuryRiskAlerts.tsx | Adds descent-load red-flag channel + AMS red-flag channel
Summary tab | PerformanceSnapshot | ✅ Preserve | — | src/components/PerformanceSnapshot.tsx | CTL / ATL / TSB / ACWR scale bars. Reads existing CoachSnapshot.
Summary tab | TRIMPBreakdown | 🔄 Extend | S8 | src/components/TRIMPBreakdown.tsx | New eccentricDose series stacked onto existing sport-type bars
Summary tab | WhatChangedCard | 🔄 Extend | S12 | src/components/WhatChangedCard.tsx | Narrative source switches to Adaptive Plan Engine output
Summary tab | WeekAtAGlance | ✅ Preserve | — | src/components/WeekAtAGlance.tsx | 7 readiness dots. Unchanged.
Summary tab | Riley hero card | 🆕 Add | S1 (stub), S12 (real) | src/components/RileyHeroCard.tsx (new) | Wraps TodayBriefing; persona + synthesis + 'What's driving this' collapsible
Plan tab | PlanView | ✂ Streamline | S12 | src/components/PlanView.tsx | 'This week, per Riley' narration card prepended above existing list
Plan tab | WeekStrip | ✅ Preserve | — | src/components/WeekStrip.tsx | M-T-W-T-F-S-S pill strip. Unchanged.
Plan tab | WorkoutCard | 🔄 Extend | S2–S4, S5–S7, S11 | src/components/WorkoutCard.tsx | Terrain / MIM / Altitude tier-chip slots added; existing layout preserved
Plan tab | PlanCompliance | ✅ Preserve | — | src/components/PlanCompliance.tsx | % complete card. Unchanged.
Plan tab | NextWorkoutSummary | ✅ Preserve | — | src/components/NextWorkoutSummary.tsx | Unchanged.
Plan tab | Per-Riley narration card | 🆕 Add | S12 | src/components/PlanNarrationCard.tsx (new) | New card prepended above Plan list
Stats tab | CompliancePanel | 📦 Re-parent | S1 | src/components/CompliancePanel.tsx | Becomes Compliance sub-tab; no code changes
Stats tab | ReadinessPanel | 📦 Re-parent | S1 | src/components/ReadinessPanel.tsx | Becomes Readiness sub-tab; no code changes
Stats tab | PerformancePanel | 📦 Re-parent | S1 | src/components/PerformancePanel.tsx | Becomes Performance sub-tab; no code changes
Stats tab | PerformanceChart | 🔄 Extend | S4, S12 | src/components/PerformanceChart.tsx | Metric pills + race-day reference band + ACWR corridor added as optional props
Stats tab | TimeWindowToggle | ✅ Preserve | — | src/components/TimeWindowToggle.tsx | 7d / 30d / 90d / All. Unchanged.
Stats tab | PerformanceGlossary | 🔄 Extend | S7 | src/components/PerformanceGlossary.tsx | Adds MIM + Altitude + Eccentric glossary rows
Stats tab | StatCards | ✅ Preserve | — | src/components/StatCards.tsx | 4-card grid. Unchanged.
Coach tab | CoachChat | ✅ Preserve | — | src/components/CoachChat.tsx | Chat surface, pending inferences. Shell untouched.
Coach tab | CoachInsightCard | 🔄 Extend | S7, S11 | src/components/CoachInsightCard.tsx | Citation chips + AMS advisory variant added
Coach tab | CoachHistory | ✅ Preserve | — | src/components/CoachHistory.tsx | History + minimize controls. Unchanged.
Coach tab | CoachPersonaSelector | ✅ Preserve | — | src/components/CoachPersonaSelector.tsx | Shared with Settings. Unchanged.
Coach tab | Riley avatar coin in header | 🆕 Add | S12 | src/components/RileyAvatar.tsx (new) | Visual-only; no new data
Settings tab | ProfileCard | ✅ Preserve | — | src/components/ProfileCard.tsx | Unchanged.
Settings tab | CoachPersonaSelector | ✅ Preserve | — | src/components/CoachPersonaSelector.tsx | 4-button grid (Riley/Sam/Max/Zen). Unchanged.
Settings tab | AboutMeEditor | ✅ Preserve | — | src/components/AboutMeEditor.tsx | Free-text field consumed by every Riley reply. Unchanged.
Settings tab | HRZoneEditor | ✅ Preserve | — | src/components/HRZoneEditor.tsx | Max HR + 5 zone bands + Garmin LTHR sync. Unchanged.
Settings tab | IntegrationsRow | 🔄 Extend | S10 | src/components/IntegrationsRow.tsx | Zwift row label upgraded from 'optional' to 'recommended for altitude prep'
Settings tab | CacheDiagnostics | ✅ Preserve | — | src/components/CacheDiagnostics.tsx | Unchanged.
Settings tab | PrivacyRow | ✅ Preserve | — | src/components/PrivacyRow.tsx | Data export / delete. Unchanged.
Settings tab | Trips + Altitude Wizard | 🆕 Add | S11 | src/components/TripsSection.tsx, AltitudeWizard.tsx (new) | Wizard trigger + trip auto-detect from calendar
Settings tab | Methodology link → Screen 12 | 🆕 Add | S13 | src/components/MethodologyView.tsx (new) | 'How the 5 engines work' explainer
Shared primitives | ReadinessBadge / TierChip / SparklineMini / MetricCard / ScaleBar / Navbar | ✅ Preserve | — | src/components/*.tsx (primitives) | All primitives ship unchanged
Shared utils | readiness.ts (ATE + Plews + Meeusen) | ✅ Preserve | — | src/utils/readiness.ts | Already T1/T2 sourced. Untouched.
Shared utils | trimp.ts (Banister TRIMP + static MIM_MATRIX + DOMS_CARRY) | 🔄 Extend | S5, S8 | src/utils/trimp.ts | MIM_MATRIX gains Bayesian posterior path; DOMS_CARRY extended by eccentric-TRIMP. Static matrix kept as cold-start fallback.
Shared utils | garmin.ts (athlete-scoped storage, tz fetch) | ✅ Preserve | — | src/utils/garmin.ts | Unchanged.
Shared utils | types/index.ts (732 LOC) | 🔄 Extend | every sprint | src/types/index.ts | Only additive: new engine types appended. No existing types renamed or removed.
Shared tests | 12 existing test files | ✅ Preserve | every sprint (DoD gate) | src/__tests__/ | trimp / readiness / zones / targets / compliance / matching / performance / plan-data / raceProjection / coachAnalyticsSnapshot / coachInsightCache / coachPingTriggers must stay green at every DoD
Backend | api/coach/ (Python serverless) | 🔄 Extend | S12 | api/coach/ | Adds engine-state payload; prompt template stays backward-compatible
Backend | api/garmin/ · api/apple/ · api/auth/ | ✅ Preserve | — | api/garmin/, api/apple/, api/auth/ | Unchanged.
Backend | worker/strava-token-exchange.ts (Cloudflare) | ✅ Preserve | — | worker/strava-token-exchange.ts | Unchanged.
Infra | ios/BrokenArrowHealth/ (SwiftUI + HealthKit) | ✅ Preserve | — | ios/BrokenArrowHealth/ | No iOS work in this plan.
Infra | deploy.yml (GitHub Actions) | 🔄 Extend | S1 | .github/workflows/deploy.yml | Coverage gate raised to 80/80/80/80; no other job changes
Summary
Preserve | 24
Extend | 13
Re-parent | 3
Streamline | 1
Add | 5
Deprecate | 0
TOTAL | 46
Key commitments
· 0 deprecations — no shipped component is being replaced.
· All 12 shipped test files must stay green at every sprint's Definition-of-Done.
· Static MIM_MATRIX retained as cold-start fallback alongside new Bayesian posterior.
· CoachSnapshot type additions are append-only — no existing fields renamed or removed.
· All 5 Settings rows (Profile / CoachPersona / AboutMe / HRZone / Integrations / CacheDiagnostics / Privacy) ship as-is; plan only ADDS Trips + Methodology.

## User_Stories
User Stories (INVEST form)
ID | Sprint | Persona | Story (As a X, I want Y so that Z) | Priority | Points | Status
US-S1-01 | 1 | Developer | Single src/engines/ module boundary so engine code stays separable from UI | Must | 3 | Planned
US-S1-02 | 1 | Developer | Typed FeatureStore interface so every engine consumes a consistent shape | Must | 5 | Planned
US-S1-03 | 1 | Developer | DEM adapter interface so DEM sources can be swapped without touching engines | Must | 3 | Planned
US-S1-04 | 1 | Developer | Evidence-tier system so every engine coefficient can be tagged T1-T4 | Must | 2 | Planned
US-S1-05 | 1 | Developer | Coverage gating enforced in CI | Must | 2 | Planned
US-S2-01 | 2 | Athlete | Trail pace normalised to flat-equivalent GAP | Must | 5 | Planned
US-S2-02 | 2 | Athlete | GAP shown next to raw pace in activity view | Must | 2 | Planned
US-S3-01 | 3 | Athlete | Elevation gain matches reality (+/-3%), not barometer drift | Must | 8 | Planned
US-S3-02 | 3 | Developer | DEM tile caching so hot routes don't re-fetch | Should | 3 | Planned
US-S4-01 | 4 | Athlete | Vertical Efficiency tracked so power-hiking improvement is visible | Must | 5 | Planned
US-S4-02 | 4 | Athlete | UTMB Index estimate based on recent races | Should | 5 | Planned
US-S5-01 | 5 | Data-aware dev | Population priors fit from fleet data | Must | 8 | Planned
US-S5-02 | 5 | Developer | Bayesian partial-pooling posterior computation | Must | 8 | Planned
US-S5-03 | 5 | PM | MIM shadow-mode alongside legacy, no UI change yet | Must | 3 | Planned
US-S6-01 | 6 | Athlete | Post-session soreness prompt after strength/descent days | Must | 3 | Planned
US-S6-02 | 6 | Athlete | MIM personalised after ~20 same-sport sessions | Must | 8 | Planned
US-S6-03 | 6 | Developer | Cohort rollout service for feature-flag variants | Must | 5 | Planned
US-S7-01 | 7 | Athlete | Each MIM coefficient shows evidence tier and source | Must | 5 | Planned
US-S7-02 | 7 | Developer | MIM methodology doc (OpenSim -> GRADE -> partial pooling) | Must | 3 | Planned
US-S7-03 | 7 | PM | All cohorts flipped to active after evidence-tier UI ships | Must | 2 | Planned
US-S8-01 | 8 | Athlete | Eccentric load quantified per activity (descent buckets) | Must | 5 | Planned
US-S8-02 | 8 | Athlete | Eccentric TRIMP added to daily total but tagged separately | Must | 3 | Planned
US-S9-01 | 9 | Athlete | Second downhill bout counted as less damaging (repeated-bout) | Should | 5 | Planned
US-S9-02 | 9 | Developer | engines.descent.boutMemory in CoachSnapshot | Must | 2 | Planned
US-S9-03 | 9 | Athlete | Readiness raises RED earlier on back-to-back eccentric days | Should | 3 | Planned
US-S10-01 | 10 | Athlete | Time-at-altitude tracked for acclimatization state | Must | 5 | Planned
US-S10-02 | 10 | Athlete | Acclimatization state shown on 0-100 scale | Must | 5 | Planned
US-S11-01 | 11 | Athlete | Prescribed paces slowed at altitude | Must | 5 | Planned
US-S11-02 | 11 | Athlete | AMS advisory on rapid ascent to high altitude | Should | 3 | Planned
US-S11-03 | 11 | Developer | engines.altitude fully plugged into CoachSnapshot | Must | 2 | Planned
US-S12-01 | 12 | Athlete | One clear daily prescription respecting all 5 engines | Must | 8 | Planned
US-S12-02 | 12 | Athlete | Why-this-workout card showing per-engine contributions | Must | 5 | Planned
US-S12-03 | 12 | Developer | LLM coach grounded strictly on CoachSnapshot.engines | Must | 5 | Planned
US-S13-01 | 13 | User | App loads fast with long history (p95 < 250 ms) | Must | 5 | Planned
US-S13-02 | 13 | User | Graceful offline/poor-connectivity degradation | Must | 3 | Planned
US-S13-03 | 13 | User | Accessibility (axe-core clean, colour-blind safe) | Must | 3 | Planned
US-S13-04 | 13 | Developer | Full release checklist + v1.0.0 tag | Must | 3 | Planned

## Acceptance_Criteria
Acceptance Criteria (Gherkin: Given / When / Then)
Story ID | AC # | Given | When | Then
US-S1-01 | 1 | repo state at sprint start | I open src/engines/index.ts | it re-exports readiness, mim, terrain, descent, altitude namespaces
US-S1-01 | 2 | src/engines/readiness/ exists | I compare to existing src/utils/readiness.ts | existing symbols re-exported with no behaviour change (trimp.test.ts, readiness.test.ts still green)
US-S1-02 | 1 | a fresh FeatureStore | I write+read daily/activity/athlete/elevationTile/hypoxicExposure/eccentricBucket records | round-trip is lossless
US-S1-03 | 1 | Open-Elevation adapter mock | DEMAdapter.lookup(lat, lon) is called | it returns an ElevationSample within expected shape
US-S1-04 | 1 | an EvidenceTier union in code | I wrap a MIM matrix entry in TieredValue<number> | tier and citation are visible at the call site
US-S1-05 | 1 | vitest.config.ts with coverage thresholds at 80 | I drop below 80% in a PR | CI fails the coverage step
US-S2-01 | 1 | an activity with altitude + time streams | computeGAP(activity) runs | GAP >= pace for net-uphill, <= pace for net-downhill (+/-2% vs hand-computed fixture)
US-S2-01 | 2 | a flat activity (¦grade¦<1%) | computeGAP runs | GAP ~= pace within 0.5%
US-S2-01 | 3 | Minetti 2002 polynomial in code | a reviewer reads minetti.ts header | the PMID 12235031 citation is present
US-S2-02 | 1 | an activity with GAP computable | the Activity card renders | GAP is shown next to raw pace
US-S2-02 | 2 | an activity without altitude stream | the Activity card renders | GAP field shows '-' (not 0 or NaN)
US-S3-01 | 1 | an activity with lat/lon stream and DEM coverage | correctElevation(activity) runs | gain is within 3% of a known-good reference
US-S3-01 | 2 | no DEM coverage available | correction is attempted | original stream returned with correctionApplied=false
US-S3-02 | 1 | tile cache with LRU and TTL | cache capacity is exceeded | oldest tiles evicted in LRU order
US-S4-01 | 1 | an activity + athlete | computeVE(activity, athlete) runs | it returns {vamMPerHour, crossoverGrade, runRatio}
US-S4-01 | 2 | Giovanelli 2016 crossover | crossover grade is computed | value lies within 15.8deg-22deg range
US-S4-02 | 1 | a set of recent races | estimateUTMBIndex(athlete, races) runs | result includes {value, confidence, method, citations}
US-S5-01 | 1 | >=30 athletes x 12 weeks of data | fit-mim-priors.ts runs | priors.json is produced with per-sport mu/sigma/tier/citation/sampleSize
US-S5-02 | 1 | an athlete with zero observations | computeMIMPosterior runs | posterior equals prior
US-S5-02 | 2 | an athlete with >30 observations | computeMIMPosterior runs | posterior mean within 10% of raw athlete mean
US-S5-03 | 1 | ENGINES_MIM_BAYES=shadow flag | daily compute runs | delta (new-legacy) logged, no UI/prescription change
US-S6-01 | 1 | a completed strength_lower or descent-heavy activity yesterday | the athlete opens the app today | a 1-10 soreness prompt is shown (skippable)
US-S6-02 | 1 | nightly posterior update job | cron trigger fires | posterior is re-computed idempotently
US-S6-02 | 2 | >=20 observations for a sport | MIM posterior is read | tier upgrades from T3 to T2 in the UI
US-S6-03 | 1 | cohort config in config/cohorts.json | FeatureFlagService.variant('mim-bayes', athleteId) is called | it returns 'shadow' ¦ 'active' ¦ 'legacy'
US-S7-01 | 1 | a MIM coefficient in the UI | the athlete hovers/taps | {tier, citation, sampleSize, posteriorSD} is surfaced
US-S7-01 | 2 | evidence tiers | a badge renders | T1=green, T2=blue, T3=amber, T4=grey with non-colour icon
US-S7-02 | 1 | MIM methodology doc | a new contributor reads it | they can find inputs, priors, shrinkage, per-user learning, tier rules, worked example
US-S7-03 | 1 | evidence-tier UI shipped | canary rollout is enabled | 10%->50%->100% over 48h with rollback runbook
US-S8-01 | 1 | an activity with descent segments | computeEccentricTRIMP(activity) runs | it returns {eccTRIMP, buckets:{mild,moderate,severe}} per Vernillo 2017
US-S8-02 | 1 | a TRIMPRecord | eccentric fields are read | eccentricTRIMP and eccentricBuckets present; legacy paths default to 0
US-S9-01 | 1 | two severe-descent bouts within 10 days | bout_n_dose is computed for the second bout | dose is discounted by the decay factor
US-S9-02 | 1 | descent engine outputs | CoachSnapshot is assembled | engines.descent.boutMemory = {lastSevereDate,lastModerateDate,protectionFactor}
US-S9-03 | 1 | eccTRIMP last 48h > athlete p75 | readiness threshold is evaluated (flag on) | RED threshold tightens by 0.1 points and is logged
US-S10-01 | 1 | exposure records | computeHypoxicDose(exposures) runs | returns {kmHoursAbove1500m, kmHoursAbove2500m}
US-S10-02 | 1 | ~2 weeks at 2000-2500m with sufficient dose | acclimatizationIndex is computed | index approaches 50 asymptotically
US-S10-02 | 2 | athlete returns to sea level | index is recomputed over 2-3 weeks | index decays monotonically toward baseline
US-S11-01 | 1 | prescription + altitude + acclimatization index | dampenPrescription runs | paces slowed per West 2013 (~1% VO2max per 100m >1500m), never sped up
US-S11-02 | 1 | ascentRate>500m/day AND currentAlt>3000m | Bailey 2021 consensus is evaluated | AMS advisory surfaced as informational (no workout block)
US-S11-03 | 1 | altitude engine outputs | CoachSnapshot is assembled | engines.altitude = {currentAltM, acclimatizationIndex, intensityDampening, amsAdvisory}
US-S12-01 | 1 | athlete + date with 5 engines populated | adaptivePlan runs | returns {sessionType, duration, intensityZones, intensityCeiling, caveats, explanations}
US-S12-02 | 1 | a daily prescription | the dashboard renders | Why-this-workout card shows one explanation per engine with tier badge
US-S12-03 | 1 | 10 fixture days | LLM coach output is generated | engine values cited match snapshot exactly (goldens pass)
US-S13-01 | 1 | a 2-year-history athlete | daily compute runs | p95 < 250 ms
US-S13-02 | 1 | poor connectivity | app opens | last CoachSnapshot cached; stale>24h banner shown; no blank UI on API failure
US-S13-03 | 1 | axe-core CI job | the build runs | zero critical accessibility violations
US-S13-04 | 1 | end of Sprint 13 | release checklist completed | v1.0.0 tag pushed; CHANGELOG synthesised; deploy workflow green

## Tasks
Engineering Tasks (for Claude Code, with file paths)
Sprint | Task ID | Area | Description | File Path(s) | Status
1 | T1.1 | Arch | Create src/engines/ subfolders + index.ts re-exports | src/engines/{readiness,mim,terrain,descent,altitude}/ | Planned
1 | T1.2 | Types | FeatureStore interface + InMemoryFeatureStore | src/engines/featureStore.ts | Planned
1 | T1.3 | Adapter | DEMAdapter interface + Open-Elevation adapter + stubs | src/engines/adapters/*.ts | Planned
1 | T1.4 | Types | EvidenceTier + TieredValue<T> | src/engines/evidence.ts | Planned
1 | T1.5 | CI | Coverage thresholds 80/80/80/80 + enforce on CI | vitest.config.ts + .github/workflows/deploy.yml | Planned
1 | T1.6 | Docs | ADR 0001 engine layout + ADR 0002 evidence tiers | docs/adr/0001-engine-module-layout.md, docs/adr/0002-evidence-tiers.md | Planned
1 | T1.7 | Obs | Structured logging via debug with ba:engine:* prefix | src/engines/* | Planned
1 | T1.8 | Docs | README Quickstart + PR template | README.md, .github/PULL_REQUEST_TEMPLATE.md | Planned
2 | T2.1 | Engine | Minetti cost-of-locomotion polynomial (grade -45..+45%) | src/engines/terrain/minetti.ts | Planned
2 | T2.2 | Engine | computeGAP(activity) with guardrails | src/engines/terrain/gap.ts | Planned
2 | T2.3 | UI | Render GAP next to pace on ActivityCard | src/components/ActivityCard.tsx | Planned
2 | T2.4 | Snapshot | Populate CoachSnapshot.engines.terrain.gap | src/utils/coachSnapshot.ts | Planned
2 | T2.5 | Fixture | Broken Arrow 26K activity fixture JSON | src/__tests__/fixtures/broken-arrow-26k.json | Planned
3 | T3.1 | Engine | correctElevation orchestrator + region dispatch | src/engines/terrain/dem.ts | Planned
3 | T3.2 | Adapter | USGS 3DEP, SRTM, ASTER GDEM adapters | src/engines/adapters/{usgs3DEP,srtm,asterGDEM}.ts | Planned
3 | T3.3 | Perf | LRU tile cache + TTL | src/engines/terrain/tileCache.ts | Planned
3 | T3.4 | Infra | Cloudflare Worker DEM proxy (CORS) | worker/dem-proxy.ts | Planned
3 | T3.5 | Integration | GAP prefers DEM-corrected stream | src/engines/terrain/gap.ts | Planned
4 | T4.1 | Engine | Vertical Efficiency + Giovanelli crossover table | src/engines/terrain/{ve,giovanelli}.ts | Planned
4 | T4.2 | Engine | UTMB Index estimator | src/engines/terrain/utmbIndex.ts | Planned
4 | T4.3 | Engine | ITRA Performance Index fallback | src/engines/terrain/itraIndex.ts | Planned
4 | T4.4 | UI | Terrain card on DashboardView | src/components/DashboardView.tsx | Planned
4 | T4.5 | Docs | README race-ready metrics section | README.md | Planned
5 | T5.1 | Data | scripts/fit-mim-priors.ts (hashed-athlete fleet fit) | scripts/fit-mim-priors.ts | Planned
5 | T5.2 | Data | priors.json output artifact | src/engines/mim/priors.json | Planned
5 | T5.3 | Engine | Bayesian posterior (Efron-Morris / Gelman BDA3) | src/engines/mim/bayes.ts | Planned
5 | T5.4 | Routing | computeMIM dispatches legacy vs Bayes by flag | src/engines/mim/index.ts | Planned
5 | T5.5 | Obs | Shadow-mode delta logging (10% sample) | src/engines/mim/shadow.ts | Planned
5 | T5.6 | Docs | docs/notebooks/mim-priors.md worked example | docs/notebooks/mim-priors.md | Planned
6 | T6.1 | UI | SorenessPrompt component + hook | src/components/SorenessPrompt.tsx | Planned
6 | T6.2 | API | Vercel cron: update-posteriors.py (chunked, idempotent) | api/mim/update-posteriors.py | Planned
6 | T6.3 | Engine | Observation -> posterior update learner | src/engines/mim/learner.ts | Planned
6 | T6.4 | Infra | FeatureFlagService cohort variants | src/services/featureFlags.ts, config/cohorts.json | Planned
6 | T6.5 | Release | Flip 5 opt-in athletes to active variant | config/cohorts.json | Planned
7 | T7.1 | UI | MIMEvidenceBadge with aria + icon + colour | src/components/MIMEvidenceBadge.tsx | Planned
7 | T7.2 | Types | Extend MIMPosterior with tier/citation/sampleSize/posteriorSD | src/engines/mim/types.ts | Planned
7 | T7.3 | Docs | MIM methodology doc (~2000 words, worked example) | docs/mim-methodology.md | Planned
7 | T7.4 | Release | Canary 10%->50%->100% over 48h | config/cohorts.json | Planned
7 | T7.5 | Docs | Rollback runbook | docs/runbooks/mim-rollback.md | Planned
8 | T8.1 | Engine | Eccentric TRIMP with Vernillo 2017 buckets | src/engines/descent/eccentric.ts | Planned
8 | T8.2 | Types | Extend TRIMPRecord with eccentric fields | src/types/index.ts | Planned
8 | T8.3 | Integration | CTL/ATL/TSB optional eccentric upweight | src/utils/trimp.ts | Planned
8 | T8.4 | UI | Eccentric load strip on Load tab | src/components/LoadTab.tsx | Planned
8 | T8.5 | Snapshot | engines.descent.eccentricTRIMP in CoachSnapshot | src/utils/coachSnapshot.ts | Planned
9 | T9.1 | Engine | Repeated-bout decay (Hyldahl 2017) | src/engines/descent/boutMemory.ts | Planned
9 | T9.2 | Integration | Descent engine composition | src/engines/descent/index.ts | Planned
9 | T9.3 | Integration | Readiness accepts EccentricSignal (flagged) | src/engines/readiness/integration.ts | Planned
9 | T9.4 | Docs | ADR 0003 descent engine | docs/adr/0003-descent-engine.md | Planned
10 | T10.1 | Engine | Hypoxic dose accumulator | src/engines/altitude/dose.ts | Planned
10 | T10.2 | Engine | Acclimatization sigmoid (Levine 1997 / Chapman 2014) | src/engines/altitude/acclimatization.ts | Planned
10 | T10.3 | UI | AltitudeTripForm manual entry | src/components/AltitudeTripForm.tsx | Planned
10 | T10.4 | iOS | HealthKit altitude exporter stub | ios/BrokenArrowHealth/AltitudeExporter.swift | Planned
10 | T10.5 | UI | Acclimatization strip on dashboard | src/components/DashboardView.tsx | Planned
11 | T11.1 | Engine | VO2max-loss dampening (West 2013) | src/engines/altitude/dampening.ts | Planned
11 | T11.2 | Engine | AMS advisory (Bailey 2021 consensus) | src/engines/altitude/ams.ts | Planned
11 | T11.3 | Snapshot | engines.altitude full object in CoachSnapshot | src/utils/coachSnapshot.ts | Planned
11 | T11.4 | Legal | AMS advisory copy review (informational, not medical) | src/components/AmsAdvisory.tsx | Planned
12 | T12.1 | Engine | adaptivePlan(athlete, date) ensemble | src/engines/adaptive/index.ts | Planned
12 | T12.2 | Docs | ADR 0004 adaptive-plan priority rules | docs/adr/0004-adaptive-plan.md | Planned
12 | T12.3 | UI | Why-this-workout card | src/components/WhyThisWorkout.tsx | Planned
12 | T12.4 | LLM | Coach prompt rewrite + golden tests | src/prompts/coach.ts, src/__tests__/coachGolden.test.ts | Planned
13 | T13.1 | Perf | tinybench suite + memoisation | bench/*.bench.ts | Planned
13 | T13.2 | Offline | Service-worker + CoachSnapshot cache + stale banner | src/sw.ts, src/components/StaleBanner.tsx | Planned
13 | T13.3 | a11y | axe-core CI job + fix violations | .github/workflows/a11y.yml | Planned
13 | T13.4 | Docs | Release runbook v1 + CHANGELOG synthesis | docs/runbooks/release-v1.md, CHANGELOG.md | Planned
13 | T13.5 | Release | Version bump to 1.0.0 and tag v1.0.0 | package.json + git tag | Planned

## QA_Checklist
QA/QC Checklist (per sprint)
Sprint | Area | Item | Status
1 | CI | npm ci && npm run lint && npm test green locally and on CI | Open
1 | Coverage | >=80% on new src/engines/ | Open
1 | Regression | All existing 12 test files unchanged | Open
1 | Docs | ADR 0001 and 0002 reviewed | Open
1 | UX | No user-facing change (smoke: readiness still renders) | Open
1 | Release | git tag v0.1.0 on merge | Open
2 | Science | Minetti polynomial uses published coefficients with PMID 12235031 comment | Open
2 | Fixture | Real-world fixture (Broken Arrow 26K) included | Open
2 | UX | GAP label + tooltip citing Minetti 2002 | Open
2 | Safety | No negative GAP, NaN, or Infinity; runtime assertions | Open
2 | Perf | GAP on 7,200-sample activity < 50 ms | Open
3 | Adapter | Mock HTTP for every adapter path | Open
3 | Cache | LRU eviction and TTL verified | Open
3 | Region | US->3DEP, non-US 60S-60N->SRTM, polar->ASTER, fallback->Open-Elevation | Open
3 | Obs | Every correction logs {activityId, gainBefore, gainAfter, pctDelta, source} | Open
3 | Failure | 500/timeout/malformed payloads tested | Open
4 | Science | Giovanelli 2016 crossover cited (PMID 27116915) | Open
4 | Science | UTMB/ITRA validated on 3 published athlete profiles | Open
4 | UX | VE trend uses 4-week rolling window | Open
4 | Privacy | No PII leaks in ITRA fallback | Open
4 | LLM | engines.terrain.ve available in coach prompt | Open
5 | Data | Priors notebook reproducible (seed + sample sizes recorded) | Open
5 | Math | Shrinkage monotonicity tested on synthetic fleets | Open
5 | Release | Flag defaults OFF in production | Open
5 | Privacy | Priors use hashed athlete IDs; no PII | Open
5 | Obs | Shadow delta sampled to 10% of days | Open
6 | UX | Soreness prompt tested on mobile and desktop | Open
6 | Cron | update-posteriors idempotent (re-run -> identical output) | Open
6 | TZ | Soreness observations aligned with athlete tz | Open
6 | Release | Manual dry-run before cohort flip | Open
6 | Rollback | Flag=shadow restores S5 state | Open
7 | Content | Tooltip content human-cross-checked vs source papers | Open
7 | a11y | Keyboard-reachable tooltips; colour-blind-safe badges (icon+colour) | Open
7 | Review | Methodology doc peer-reviewed (or T4-flagged otherwise) | Open
7 | Runbook | Rollback performed in staging | Open
7 | Release | Canary 10/50/100 over 48h | Open
8 | Science | Vernillo 2017 bucket boundaries cited exactly (PMID 28497285) | Open
8 | Math | Pace-penalty monotonically increasing with ¦grade¦ | Open
8 | Regression | trimp.test.ts unchanged for flat activities | Open
8 | Fixture | BA 26K -> eccTRIMP > 0; flat 10K -> eccTRIMP = 0 | Open
8 | Units | Eccentric TRIMP printed with Banister TRIMP precision | Open
9 | Science | Hyldahl 2017 half-life default (10d, PMID 28457071) | Open
9 | Flag | Readiness nudge behind feature flag | Open
9 | Rule | Severity-matched protection only | Open
9 | Stability | CTL/ATL/TSB numerically stable | Open
9 | UX | Eccentric carry-over chip explains nudge to athlete | Open
10 | Science | Levine 1997 + Chapman 2014 cited in sigmoid source | Open
10 | Math | Sea-level decay curve tested | Open
10 | Edge | Altitude-native athlete baseline handled | Open
10 | TZ | Exposure timestamps tz-safe | Open
10 | UX | Manual altitude-trip entry first-class | Open
11 | Science | West 2013 VO2max-loss curve plotted vs published data | Open
11 | Safety | Dampening is one-way (never sped up) | Open
11 | Legal | AMS advisory copy legally reviewed ('advisory, not medical') | Open
11 | UX | No auto-cancellation of workouts | Open
11 | Personal | Dampening shrunk by acclimatizationIndex/100 for altitude-natives | Open
12 | Precedence | Rule precedence explicit; no ambiguity | Open
12 | Safety | No rule up-prescribes beyond readiness ceiling | Open
12 | Golden | 10 scenario goldens (hard after green, rest after red, altitude-travel, etc.) | Open
12 | LLM | Blind review 10 coach outputs >= 9/10 pass | Open
12 | Docs | ADR 0004 merged | Open
13 | Perf | p95 daily compute < 250 ms; queries > 100 ms indexed/memoised | Open
13 | Offline | CoachSnapshot cached; banner when stale > 24h | Open
13 | a11y | axe-core zero criticals; Lighthouse >= 90 on all axes | Open
13 | Load | 500 concurrent athletes adaptive plan in < 2 s total | Open
13 | Privacy | No PII in logs; T4 items reviewed | Open
13 | Release | package.json 1.0.0; git tag v1.0.0; deploy workflow green | Open

## Test_Matrix
Test Matrix (Unit / Integration / Regression / Golden / E2E / Perf / a11y)
Sprint | Layer | File / Suite | What it asserts
1 | Unit | featureStore.test.ts | round-trip, overwrite, time-range query
1 | Unit | evidence.test.ts | tier ordering, citation string invariant
1 | Unit | demAdapter.openElevation.test.ts | HTTP mock 200/404/timeout
1 | Regression | existing 12 test files | all still green after refactor
2 | Unit | minetti.test.ts | 10 grade points vs published table
2 | Unit | gap.test.ts | 6 fixtures inc flat, up5, up10, down5, rolling, bad-data
2 | Unit | gap.perf.test.ts | 7,200-sample activity < 50 ms
2 | Integration | terrain.integration.test.ts | GAP populated into CoachSnapshot
2 | E2E | Playwright smoke | Activity card renders GAP label
3 | Unit | tileCache.test.ts | LRU eviction + TTL expiry
3 | Unit | dem.region.test.ts | region dispatch table
3 | Unit | usgs3DEP.test.ts | mock HTTP
3 | Unit | srtm.test.ts | mock HTTP
3 | Integration | demCorrection.integration.test.ts | BA 26K gain within 3% of published
3 | Regression | gap.test.ts | GAP correct when DEM correction applied
4 | Unit | ve.test.ts | crossover at 15.8, 22, edge grades
4 | Unit | utmbIndex.test.ts | 3 known-athlete fixtures
4 | Unit | itraIndex.test.ts | fallback path
4 | Integration | terrain.full.integration.test.ts | GAP + DEM + VE + UTMB populated
4 | Snapshot | DashboardView.test.tsx | terrain card renders
5 | Unit | bayes.test.ts | 6 synthetic fleets, shrinkage monotonicity
5 | Unit | priors.schema.test.ts | JSON schema valid
5 | Integration | mim.shadow.integration.test.ts | both paths produce sensible values
5 | Regression | trimp.test.ts | behaviour unchanged with flag OFF
6 | Unit | learner.test.ts | observation update monotonicity
6 | Component | SorenessPrompt.test.tsx | render, submit, skip
6 | Integration | mim.learner.integration.test.ts | 25 obs shrink posterior sd
6 | API | update-posteriors.test.py | pytest against fixture DB
6 | Regression | full suite | must stay green
7 | Component | MIMEvidenceBadge.test.tsx | all 4 tier variants render
7 | Visual | Storybook snapshot | 4 badges
7 | Integration | mim.full.integration.test.ts | badge renders with real posterior
7 | Doc | lint-citations.test.ts | every PMID in methodology resolves
8 | Unit | eccentric.test.ts | 3 bucket boundaries + 2 real activity fixtures
8 | Regression | trimp.test.ts | flat-only unchanged
8 | Integration | descent.integration.test.ts | CTL/ATL/TSB numerically stable
9 | Unit | boutMemory.test.ts | decay correctness
9 | Integration | descent.full.integration.test.ts | eccentric+bout+readiness nudge
9 | Regression | readiness.test.ts | unchanged when flag OFF
10 | Unit | dose.test.ts | sea-level dose = 0
10 | Unit | acclimatization.test.ts | sigmoid monotonicity, decay rate
10 | Component | AltitudeTripForm.test.tsx | submit + validation
10 | Integration | altitude.integration.test.ts | dose -> index -> snapshot
11 | Unit | dampening.test.ts | curve at 1500/2500/3500 m
11 | Unit | ams.test.ts | threshold crossings
11 | Integration | altitude.full.integration.test.ts | end-to-end dose -> advisory
11 | Regression | readiness.test.ts | unaffected at sea level
12 | Unit | adaptive.rules.test.ts | rule precedence table
12 | Golden | coachGolden.test.ts | 10 fixture days, snapshot-compared
12 | Integration | adaptive.full.integration.test.ts | all 5 engines -> prescription
12 | Regression | full suite | no prior test breaks
13 | Performance | tinybench suite | under budgets
13 | a11y | axe-core CI | 0 criticals
13 | Smoke | Playwright | login -> dashboard -> activity -> plan
13 | Regression | full suite | 0 failures

## Risk_Register
Risk Register (plan-level + sprint-level)
Risk ID | Scope | Risk | Prob | Impact | Owner | Mitigation | Status
R-P-01 | Plan | Insufficient fleet data for MIM priors | H | H | Mike | Tag low-N priors T4; ship with legacy fallback | Monitor
R-P-02 | Plan | DEM bandwidth costs | M | M | Mike | Tile cache + Cloudflare Worker proxy | Monitor
R-P-03 | Plan | Coach LLM hallucinates engine values | M | H | Mike | Golden tests + explicit prompt + post-hoc validator | Monitor
R-P-04 | Plan | Soreness-prompt fatigue hurts compliance | M | M | Mike | Cap 3/week + smart skip | Monitor
R-P-05 | Plan | Medical-liability language in AMS advisory | M | H | Mike | Legal copy review; informational framing | Monitor
R-P-06 | Plan | Scope creep into Readiness / Terra / billing | H | M | Mike | Explicit out-of-scope list; backlog anything new | Monitor
R-P-07 | Plan | CI flakiness masks real regressions | M | M | Claude | docs/flaky-tests.md + 1-sprint fix SLA | Monitor
R-P-08 | Plan | Privacy leak via cross-athlete analytics | L | H | Mike | Hashed IDs + per-sprint privacy review | Monitor
R-P-09 | Plan | Perf regression from engine stack | M | H | Claude | Perf budgets enforced from S12 | Monitor
R-P-10 | Plan | a11y backlog at release | M | M | Mike | axe-core in CI from S1; sweep in S13 | Monitor
R-P-11 | Plan | iOS HealthKit altitude path unreliable | H | M | Mike | Manual altitude-trip form as first-class UX | Monitor
R-P-12 | Plan | Dependency drift over 6 months | M | M | Claude | Renovate / Dependabot monthly | Monitor
R-S1-1 | S1 | Refactor breaks hidden imports | M | H | Claude | Add coverage gate first, refactor second | Open
R-S1-2 | S1 | Open-Elevation rate-limits dev | L | M | Claude | Mock adapter; cache real calls | Open
R-S2-1 | S2 | Elevation stream drift/spikes | H | M | Claude | Rolling 5-sample median smoothing before GAP | Open
R-S2-2 | S2 | Minetti invalid beyond +/-45% | M | L | Claude | Clamp grade; warn; fallback to raw pace | Open
R-S3-1 | S3 | DEM tile bandwidth costs | M | M | Claude | Cache aggressively; batch lookups | Open
R-S3-2 | S3 | Elevation cliff at tile boundaries | M | M | Claude | Bilinear interpolation across neighbours | Open
R-S3-3 | S3 | CORS blocks browser-side DEM calls | H | H | Claude | Proxy via Cloudflare Worker (worker/dem-proxy.ts) | Open
R-S4-1 | S4 | ITRA formula not publicly documented | H | M | Mike | Approximate from published equivalencies; tag T3 | Open
R-S4-2 | S4 | Giovanelli crossover varies inter-athlete | M | L | Claude | Expose as tunable per-athlete parameter | Open
R-S5-1 | S5 | Fleet data too small for priors | H | H | Mike | Mark low-N sports T4; flag to user | Open
R-S5-2 | S5 | Shadow logs blow up analytics cost | M | M | Claude | Sample 10% of days | Open
R-S6-1 | S6 | Soreness-prompt fatigue | M | M | Mike | Cap <=3/week; smart skip after high compliance | Open
R-S6-2 | S6 | Cron timeout (Vercel 10s) | M | H | Claude | Chunk athletes in 50s; or CF Worker | Open
R-S6-3 | S6 | Posterior overfits noisy athletes | M | M | Claude | Cap shrinkage at prior_sigma*0.3 | Open
R-S7-1 | S7 | External physiologist review slips | M | M | Mike | Ship with T4 flag on unreviewed sections | Open
R-S7-2 | S7 | Canary detects regression | M | H | Claude | Runbook rollback tested in staging | Open
R-S8-1 | S8 | Pace-penalty coefficient is choice | H | M | Claude | Flag as T4; expose as tunable; revisit S11 | Open
R-S8-2 | S8 | Back-compat break with stored TRIMPRecord | M | H | Claude | Migration: default 0; schema versioning | Open
R-S9-1 | S9 | Readiness nudge hurts compliance | M | M | Mike | Eccentric carry-over chip explains | Open
R-S9-2 | S9 | Bout memory overwrites user judgment | M | L | Claude | Never auto-skip; only tighten recommendation | Open
R-S10-1 | S10 | No HealthKit altitude stream for many | H | M | Mike | Manual trip entry first-class UX | Open
R-S10-2 | S10 | Sigmoid is population-level, not personal | M | M | Claude | Mark T2; revisit post-plan | Open
R-S11-1 | S11 | Medical-liability in AMS advisory | M | H | Mike | Legal copy review; informational framing | Open
R-S11-2 | S11 | Dampening overshoots for altitude-natives | M | M | Claude | Shrink dampening by acclimatizationIndex/100 | Open
R-S12-1 | S12 | Rule precedence feels rigid | M | M | Mike | Allow athlete override; log; feed to learner | Open
R-S12-2 | S12 | LLM hallucinates numbers | M | H | Claude | Golden tests + strict prompt + post-hoc validator | Open
R-S13-1 | S13 | Perf regression from engine stack | M | H | Claude | Perf budgets enforced in CI from S12 | Open
R-S13-2 | S13 | a11y backlog exceeds sprint capacity | M | M | Mike | Defer non-critical to v1.1 backlog | Open

## References
Peer-reviewed references cited in the plan
Author(s) | Year | Title | Venue | Tier | PMID | Source
Banister EW | 1991 | Modeling elite athletic performance (TRIMP) | In: MacDougall JD, ed. Physiological Testing of the High Performance Athlete | T1 | - | Book chapter
Bailey DM et al | 2021 | Altitude training and the AMS consensus | High Alt Med Biol | T1 | 34001987 | PubMed
Chapman RF et al | 2014 | Defining the 'dose' of altitude training | J Appl Physiol 116(6):595-603 | T2 | 24264287 | PubMed
Delp SL et al | 2007 | OpenSim framework | IEEE Trans Biomed Eng 54(11):1940-1950 | T3 | 18018689 | PubMed
Efron B, Morris C | 1977 | Stein's paradox in statistics | Sci Am 236(5):119-127 | T3 | - | Journal
Gabbett TJ | 2016 | Training-injury prevention paradox (ACWR) | Br J Sports Med 50(5):273-280 | T1 | 26758673 | PubMed
Gelman A et al | 2013 | Bayesian Data Analysis 3rd ed | CRC Press | T3 | - | Book
Giovanelli N et al | 2016 | Energetics of vertical kilometer foot races | Eur J Appl Physiol | T2 | 27116915 | PubMed
Guyatt GH et al | 2008 | GRADE evidence framework | BMJ 336(7650):924-926 | T1 | 18436948 | PubMed
Hyldahl RD et al | 2017 | Mechanisms of repeated bout effect | Exerc Sport Sci Rev | T1 | 28457071 | PubMed
Levine BD, Stray-Gundersen J | 1997 | Live high train low | J Appl Physiol 83(1):102-112 | T1 | 9216968 | PubMed
Meeusen R et al | 2013 | Overtraining syndrome ECSS/ACSM consensus | Med Sci Sports Exerc | T1 | 23247672 | PubMed
Minetti AE et al | 2002 | Energy cost of walking/running at extreme slopes | J Appl Physiol 93(3):1039-1046 | T2 | 12235031 | PubMed
Morton RH et al | 1990 | Modeling human performance in running | J Appl Physiol 69(3):1171-1177 | T1 | - | Journal
Peake JM et al | 2017 | Muscle damage and inflammation during recovery | J Appl Physiol | T1 | 28153916 | PubMed
Plews DJ, Laursen PB | 2013 | HRV in elite athletes | Int J Sports Physiol Perform | T1 | 23921488 | PubMed
Vernillo G et al | 2017 | Biomechanics of uphill/downhill running | Sports Med 47:615-629 | T2 | 28497285 | PubMed
West JB | 2013 | High Altitude Medicine and Physiology 5th ed | CRC Press | T3 | - | Book

## Glossary
Glossary
Term | Definition
ACWR | Acute:Chronic Workload Ratio (Gabbett 2016)
AMS | Acute Mountain Sickness (Bailey 2021)
ATE | Readiness composite score (src/utils/readiness.ts)
ATL | Acute Training Load (~7-day EMA)
Banister TRIMP | HR-based training impulse (Banister 1991)
Bayesian partial pooling | Shrinkage toward population mean (Efron-Morris 1977 / Gelman BDA3)
CTL | Chronic Training Load (~42-day EMA)
DEM | Digital Elevation Model (USGS 3DEP / SRTM / ASTER GDEM / Open-Elevation)
Descent-Load | Eccentric muscle damage dose from downhill (Vernillo 2017)
DoD | Definition of Done
DOMS | Delayed-Onset Muscle Soreness (carry-forward in trimp.ts)
Evidence Tier | T1 RCT/meta, T2 observational, T3 first-principles, T4 heuristic
GAP | Grade-Adjusted Pace (Minetti 2002)
GRADE | Evidence-quality framework (Guyatt 2008)
ITRA | International Trail Running Association Performance Index
LHTL | Live High Train Low (Levine & Stray-Gundersen 1997)
MIM | Musculoskeletal Impact Modifier (novel IP)
NFOR | Non-Functional Overreaching (Meeusen 2013)
OpenSim | Musculoskeletal modeling framework (Delp 2007)
Repeated-Bout Effect | Subsequent bout reduced damage (Hyldahl 2017)
TSB | Training Stress Balance (CTL - ATL)
UTMB Index | Ultra-Trail Mont-Blanc race performance index
VAM | Velocita Ascensionale Media (m/hour ascent)
VE | Vertical Efficiency (Giovanelli 2016 crossover)